## Gantt
Gyrobot Gantt Chart
T0 Kickoff: 09/03/26 ¦ T1 Audit: 10/06/26 ¦ T2 PDR : 20/11/26 ¦ T3 CDR + Mini trade show : 08/01/27
Phase | Task | Owner | Start | End | Duration (days) | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11
Phase A: Scoping and Analysis | T0: Project kickoff |  | 2026-09-03 | 2026-09-03 | 1
| Update GitLab | All | 2026-09-03 | 2026-10-05 | 33
| Write the ReadMe | Simon | 2026-09-03 | 2026-09-08 | 6
| Create the various diagrams | All | 2026-09-04 | 2026-09-22 | 19
| Identify the project's HVA functions | All | 2026-09-15 | 2026-09-29 | 15
| Specifications document | Issam | 2026-09-21 | 2026-09-30 | 10
| CSR approach | Maud | 2026-09-30 | 2026-10-04 | 5
| Write the T1 technical report (Audit) | Alexandre | 2026-09-28 | 2026-10-05 | 8
| Prepare the PPT (critical path) | All | 2026-09-30 | 2026-10-05 | 6
| T1: Audit |  | 2026-10-06 | 2026-10-06 | 1
Phase B: Design and Technical Solutions | Detail the Phase T1 Gantt chart | To be defined | 2026-10-06 | 2026-10-07 | 2
| Select components and place order | Maud & Simon | 2026-09-29 | 2026-10-15 | 17
| Generate and evaluate technical solutions for each function | To be defined | 2026-10-06 | 2026-10-19 | 14
| Advance system's 3D mechanical design (sizing, architecture) | To be defined | 2026-10-13 | 2026-11-03 | 22
| Gestion PCB (Conception & Routage) | To be defined | 2026-10-06 | 2026-10-26 | 21
| Validation PCB | To be defined | 2026-10-27 | 2026-11-09 | 14
| Justify chosen technical solutions + CSR component | To be defined | 2026-11-03 | 2026-11-19 | 17
| Preliminary HVA review + technical report update (PDR) | To be defined | 2026-11-02 | 2026-11-20 | 19
| T2: PDR |  | 2026-11-20 | 2026-11-20 | 1
Phase C: Integration and HVA Validation | Detail the Phase T2 Gantt chart | To be defined | 2026-11-20 | 2026-11-21 | 2
| Test composants | To be defined | 2026-11-23 | 2026-11-27 | 5
| Manufacture / Assemblage Robot | To be defined | 2026-11-30 | 2026-12-04 | 5
| Tenir debout (Asservissement / Équilibrage) | To be defined | 2026-12-07 | 2026-12-11 | 5
| LiDAR - Acquisition & Traitement | To be defined | 2026-11-23 | 2026-12-04 | 12
| Caméra 3D & Écriture code Python (récup data) | To be defined | 2026-11-23 | 2026-12-04 | 12
| Intégration fonctionnalités Caméra + LiDAR | To be defined | 2026-12-07 | 2026-12-18 | 12
| Rendre fonctionnelle l'IHM + Rapport IHM | To be defined | 2026-12-07 | 2026-12-18 | 12
| Tout intégrer (Matériel + Logiciel) | To be defined | 2026-12-21 | 2027-01-01 | 12
| Test each function against requirements (compliance matrix) | To be defined | 2026-12-15 | 2027-01-05 | 22
| Fix identified defects | To be defined | 2027-01-04 | 2027-01-07 | 4
| Prepare HVA demonstration (CDR) + marketing video (English) | To be defined | 2026-12-15 | 2027-01-07 | 24
| Write final S1 technical report | To be defined | 2026-12-15 | 2027-01-07 | 24
| T3: CDR + Mini trade show |  | 2027-01-08 | 2027-01-08 | 1